ALDER STUDIO   /   01

# Approve the Onboarding Pilot

Decision brief • Leadership review • 18 June 2027

| 20 | 4 weeks | $6,000 |
| --- | --- | --- |
| pilot customers | learning window | spend ceiling |

THE ASK
Approve a limited onboarding pilot with Maya Chen accountable for delivery. Keep the existing platform; test a clearer welcome sequence and one checklist.

# A Small Bet With a Visible Exit

The team needs evidence before committing to a full rollout. The pilot tests completion, time to first value and support handoffs. It does not promise a revenue result.

| Today | Pilot change | Decision gate |
| --- | --- | --- |
| 3 separate setup emails | 1 sequenced checklist | Review after four weeks |
| Ownership is unclear | Named success owner | No scope expansion without review |

ALDER STUDIO   /   02

# Compare the Options

## Sample Baseline and Pilot Target

| Option | Benefit | Trade-off |
| --- | --- | --- |
| Keep the current process | No near-term delivery cost | Existing handoffs remain |
| Pilot with 20 customers | Tests the approach before a broad change | Requires four weeks and a dedicated owner |
| Rebuild immediately | Moves directly to a single experience | Commits more resources before learning |

# Recommended Option

Run the limited pilot. Use the current system, rewrite the welcome sequence and add one checklist; defer any platform migration.

| Measure | Pilot target | Source |
| --- | --- | --- |
| Setup completed within 7 days | At least 16 of 20 participants | Checklist event log |
| Support contacts in first week | Record per participant; compare with baseline | Support ticket report |
| Serious account issues | Zero unresolved at closeout | Incident log |

Presenter note: targets are proposed thresholds for this sample, not reported results.

ALDER STUDIO   /   03

# Make the Next Month Measurable

| Week | Work | Accountable owner |
| --- | --- | --- |
| 1 | Finalize copy and baseline measures | Maya • Customer success |
| 2 | Invite participants and start the pilot | Sam • Operations |
| 3 | Review exceptions and fix copy gaps | Alex • Product |
| 4 | Report findings and recommend next step | Maya • Customer success |

# Guardrails

Pause new invitations if account access is affected.

Keep the existing onboarding path available during the test.

Do not expand the pilot without reviewing the final evidence.

RECORD THE DECISION
Sponsor: Avery Kim    Outcome: Pilot proposal for review
Owner confirmed: Avery Kim    Review meeting: 21 June 2027

Design notes: Large type, strong contrast and decision-centered storytelling. Original Dazzler template, Apache-2.0. All sample facts are fictional.