DELIVERY OFFICE   /   01

# Launch With Confidence

Weekly delivery report

PORTAL RELEASE / WEEK 24 / 14–18 JUNE 2027

| 75% | $18k | 24 |
| --- | --- | --- |
| scope complete | budget remaining | days to launch |

DECISION / 21 JUNE
Approve the 20-customer pilot. Identity integration is three days late; a reviewed password fallback protects the 12 July launch.

## Cumulative Accepted Deliverables

| Workstream | Accepted / planned | Owner |
| --- | --- | --- |
| Account setup | 6 / 6 | Alex Rivera |
| Invoice history | 5 / 6 | Sam Okafor |
| Identity | 3 / 6 | Maya Chen |
| Help and training | 4 / 6 | Lena Ortiz |

DELIVERY OFFICE   /   02

# Protect the Launch Window

| 3 | 0 | 25 Jun |
| --- | --- | --- |
| tracked risks | new funding requested | pilot review |

| Risk / owner | Trigger | Response |
| --- | --- | --- |
| Identity / Maya | Access arrives after 22 June | Reviewed password fallback |
| Content / Lena | Help copy not signed off | Limit pilot to reviewed flows |
| Support / Sam | More than 5 pilot incidents | Pause new invitations |

# What Success Looks Like

Invite 20 customers, observe setup completion and review support handoffs. The sponsor receives a recorded go / revise / pause recommendation after the 25 June acceptance review.

# Risks and Response

R-03 • Identity provider access. If credentials arrive after 22 June, the pilot will use password sign-in. Maya owns the fallback; security review is booked for 23 June.

# Decision for the Sponsor

Approve the 20-customer pilot with password sign-in, subject to security review. No additional budget is requested. Priya Shah to confirm by 21 June, 15:00.

# Next Week

Finance: approve invoice totals and download wording by 21 June.

Engineering: complete pilot deployment and rollback rehearsal by 24 June.

Customer success: confirm pilot participants and support coverage by 25 June.

Design notes: Decision hierarchy, measured progress and owner-led action. Original Dazzler template, Apache-2.0. All sample facts are fictional.